## Project Charter
Project Charter
Project Title | Host an in-person fundraising banquet for School of Rock Seattle
Business Case | A fundraising banquet will serve at least 150 guests, including the client's staff, their volunteers, community members, and donors.
High-Level Work/Definition | (1) The banquet will be marketed effectively so that a majority of invited guests will show up, (2) resulting in at least $100,000.00 USD in fundraising donations for the client.
Stakeholder Register | 1) Dan Napelee, Project Sponsor, Project Team 2)Project Team Delta 3) Volunteers 4) Donors 5) Local community members/leaders 6) Client staff 7) Dr. Eric Thomas 8) School of Rock Seatle Students
High-Level Risks | The banquet may not be well-attended. The banquet may not raise enough money.
Budget | $4,500.00 USD
Dates | The event is scheduled for Thurs August 24, 2023, 6:00 PM.
Notes | - There are at least 100 donors. Add 50 additional seats for local community members/leaders, volunteers, and client staff. - The guest speaker is Dr. Eric Thomas. Dr. Thomas's speaking fee is $950. Airfare/hotel accommodations are not included in his speaking fee. - The caterer or menu should accommodate a variety of dietary restrictions - The agenda for the banquet should be 80 minutes in length. In addition to the guest speaker, your client's Executive Director is speaking, as well as a youth leader - Even though the banquet is 80 minutes long, this does not include set up and take down/clean up
WBS is on the second tab

## WBS
BANQUET
PROJECT TITLE Fundraising Banquet |  | SCHOOL OF ROCK SEATTLE
PROJECT TEAM NAMES |  | TEAM DELTA - Alexandre Correia, Danait Gebremedhin, Bobby Habtamu
WBS CODE | TASK TITLE | TASK OWNER |  | START DATE | DUE DATE |  | LINK/RESOURCE/NOTES
|  |  | BUDGET |  |  | DURATION
1.1 | Project Management
1.1.1 | Finish Project charter | Project Team | 0 | 2023-07-05 | 2023-07-14 | 8
1.1.2 | Establish communication plan | Project Team | 0 | 2023-07-14 | 2023-07-21 | 3
1.1.3 | Develop project schedule | Project Team | 0 | 2023-07-05 | 2023-07-14 | 4
1.1.4 | Risk Management Plan | Project Team | 0 | 2023-07-05 | 2023-07-14 | 3
1.2 | Event Planning
1.2.1 | Venue Selection | Project Team | 0 | 2023-07-10 | 2023-07-31
1.2.1.1 | Research potential venue | Alexandre | 0 | 2023-07-10 | 2023-07-17 | 4 | https://mountbaker.org/rentals
1.2.1.2 | Select suitable venue | Alexandre | 480 | 2023-07-17 | 2023-07-24 | 2 | https://docs.google.com/document/d/1dhSqZKW3Fw8fslkC-L386a80vwUHauAp-wR_SF3xC4U/edit?pli=1
1.2.1.3 | Coordinate with venue staff for setup | Alexandre | 700 | 2023-07-24 | 2023-07-31 | 1
1.2 | Catering
1.2.2.1 | Research potential caterers | Alexandre | 0 | 2023-07-10 | 2023-07-17 | 3
1.2.2.2 | Select caterer based on the dietary restrictionand finalize the menu | Caterer (Chipotle) | 1605 | 2023-07-31 | 2023-08-07 | 2 | https://catering.chipotle.com/
1.2.3 | Entertainment | Project Team | 0 | 2023-07-24 | 2023-07-31
1.2.3.1 | Select host and DJ | Bereket | 0 | 2023-07-24 | 2023-07-31 | 2
1.2.4 | Guest Management | Project Team | 0 | 2023-07-10 | 2023-07-31
1.2.4.1 | Select guests | Danait | 0 | 2023-07-10 | 2023-07-17 | 3
1.2.4.2 | Send invitation to guests | Danait | 0 | 2023-07-17 | 2023-07-24 | 2
1.2.4.3 | Manage special requirment like dietary restriction | Alexandre | 0 | 2023-07-24 | 410380 | 2
1.2.5 | Marketing | Project Team | 0 | 2023-07-05 | 2023-07-20
1.2.5.1 | Develop Marketing strategy | Danait | 0 | 2023-07-05 | 2023-07-07 | 5
1.2.5.2 | Design promotion material | Project Team | 0 | 2023-07-07 | 2023-07-09 | 4
1.2.5.3 | Track record of marketing performance | Danait | 0 | 2023-07-07 | 2023-07-20 | 8
1.3 | Program Planning
1.3.1 | Event Agenda | Project Team | 0 | 2023-07-10 | 2023-07-17
1.3.2 | Guest Speaker | Project Team | 0 | 2023-07-03 | 2023-07-17
1.3.2.1 | Confirm guest speaker | Bereket | 950 | 2023-07-03 | 2023-07-10 | 2
1.3.2.2 | Buy ticket and rent hotel. | Bereket | 704 | 2023-07-10 | 2023-07-17 | 2 | https://www.expedia.com/
1.3.3 | Fundraising | Project Team | 0 | 2023-07-23 | 2023-07-24 | 2
1.3.3.1 | Send out Email Newsletter | Bereket | 0 | 2023-07-03 | 2023-07-10 | 2
1.3.3.2 | Advertise Fundraiser on Social Media | Bereket | 0 | 2023-07-03 | 2023-07-10 | 1
1.3.3.3 | Add Event to the Website | Bereket | 0 | 2023-07-03 | 2023-07-10 | 1
1.3.4
1.4 | Event Logistics
1.4.1 | Set up and Clean up | Project Team | 0 | 2023-07-24 | 2023-08-24
1.4.1.1 | Arrange seating plan | Project Team | 0 | 2023-07-24 | 2023-07-24 | 1
1.4.1.2 | Decorate the venue | Project Team | 0 | 2023-07-24 | 2023-07-24 | 1
1.4.1.3 | Cleaning the venue | Venue | 0 | 2023-08-24 | 2023-08-24 | 1 | https://docs.google.com/document/d/1dhSqZKW3Fw8fslkC-L386a80vwUHauAp-wR_SF3xC4U/edit?pli=1
1.5 | Post-Event Activites
1.5.1 | Gather feedback from attendees, staff and volunteers | Project Team | 0 | 2023-08-24 | 2023-08-31 | 2
1.5.1.1 | Send out Email Suvey | Project Team | 0 | 2023-08-24 | 2023-08-31 | 1 | https://mailchimp.com/
1.5.2 | Evaluate event success to fundrasing goal | Project Team | 0 | 2023-08-24 | 2023-08-31 | 3
1.5.3 | Express gratitude to donors, speakers and volunteers | Project Team | 0 | 2023-08-24 | 2023-08-25 | 2
1.5.3.1 | Send out thank you Emails | Project Team | 0 | 2023-08-24 | 2023-08-25 | 1
1.5.4 | Archive event documentation and lesson learned | Project Team | 0 | 2023-08-24 | 2023-08-31 | 3
|  | Total Project Costs | 4439
|  | Project Budget | 4500
Note on D7: Napelee, Daniel: Who in your stakeholder register should own which tasks?
Note on I7: Dan: Cite the resource that helped you determine the costs
Note on H8: Dan: Measure in hours
Note on E18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Event occurs during non-peak hours. Hourly rate = $160, minimum 3 hours.
Note on E19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cleaning Fee (Required) - $200 Damage Deposit (Required) - $500 Total Cost = $700
Note on E27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Chipotle catering costs $10.70 per person. 150 x 10.70 = $1605
Note on E29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Host/DJ will be one of the students
Note on E41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Speaking Fee - $950
Note on E42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Flight from Lansing, MI to Seattle, WA - $398 Hotel from Aug 23 to Aug 25 (Red Roof Inn)- $306 Total = $704
Note on E52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Included in 1.2.1.3 - Professional cleaning is provided by the venue for $200.
Note on E63: Dan: Use a formula to calculate estimated costs