## Project Charter
Project Charter
Project Title | Host an in-person fundraising banquet for [insert client name]
Business Case | A fundraising banquet will serve at least 150 guests, including the client's staff, their volunteers, community members, and donors.
High-Level Work/Definition | (1) The banquet will be marketed effectively so that a majority of invited guests will show up, (2) resulting in at least $100,000.00 USD in fundraising donations for the client.
Stakeholder Register | - Dan Napelee, Project Sponsor - [Insert Names], Project Team -[Add specific names, job titles, company names, etc, if possible]
High-Level Risks
Budget | $4,500.00 USD
Dates | The event is scheduled for Thurs March 23, 2021, 6:00 PM.
Notes | - There are at least 100 donors. Add 50 additional seats for local community members/leaders, volunteers, and client staff. - The guest speaker is Dr. Eric Thomas. Dr. Thomas's speaking fee is $950. Airfare/hotel accommodations are not included in his speaking fee. - The caterer or menu should accommodate a variety of dietary restrictions - The agenda for the banquet should be 80 minutes in length. In addition to the guest speaker, your client's Executive Director is speaking, as well as a youth leader - Even though the banquet is 80 minutes long, this does not include set up and take down/clean up
WBS is on the second tab

## WBS
Google Data Analytics Certification
| No | TASK TITLE | BUDGET | DURATION | LINK/RESOURCE/NOTES
| 1.1 | Research
| 1.1.1 | Do research on the requirement and resource needed. | 0 | 1 day | Check if it require any prior knowledge and any resource the program can't provide
| 1.2 | Enroll
| 1.2.1 | Enroll in Google Data Analytics Course | 294 | 2 days | Join the program by paying prior for the next 6 month.
| 1.3 | Complete Course Modules and Quizzes
| 1.3.1 | Foundations: Data, Data, Everywhere | 0 | 11 days 2 hours per day | Foundations: Data, Data, Everywhere
| 1.3.2 | Ask Questions to Make Data-Driven Decisions | 0 | 10.5 days 2 hours per day | Ask Questions to Make Data-Driven Decisions
| 1.3.3 | Prepare Data for Exploration | 0 | 12.5 days 2 hours per day | Prepare Data for Exploration
| 1.3.4 | Process Data from Dirty to Clean | 0 | 11.5 days 2 hours per day | Process Data from Dirty to Clean
| 1.3.5 | Analyze Data to Answer Questions | 0 | 13 days 2 hours per day | Analyze Data to Answer Questions
| 1.3.6 | Share Data Through the Art of Visualization | 0 | 12 days 2 hours per day | Share Data Through the Art of Visualization
| 1.3.7 | Data Analysis with R Programming | 0 | 18 days 2 hours per day | Data Analysis with R Programming
| 1.3.8 | Google Data Analytics Capstone: Complete a Case Study | 0 | 5 days 2 hours per day | Google Data Analytics Capstone: Complete a Case Study
| 1.4 | Prepare for the Certification Exam
| 1.4.1 | Review Course Materials | 0 | 5 days | Revise all the note taken and resource provided
| 1.4.2 | Practice with Sample Question | 0 | 5 days | Rehearse questions and practical code in different website
| 1.5 | Take the Certification Exam
| 1.5.1 | Exam Time | 0 | 1 day | Take a deep breath and stay hydrated
| 1.6 | Receive Certification Results
| 1.6.1 | See your results | 0 | 1 day | Hope for an excellent result
| 1.6.2 | Share Result on Linkedln | 0 | 1 day | Let the world know your accomplishment
Note on F5: Dan: Cite the resource that helped you determine the costs